## Active
| T22 - Project Management |  | v 3.0 | Updated 18.MAR.17 by MWC
No. | Task Name | Description | Project Owner | Status | Rating | Get-to-Green Plan | Date Started | Est. Effort | Est. Date of Completion | Act. Date of Completion | Notes
1 | M2_D2 - Communication Plan | Set up a OneDrive folder for the project team, formalize our communications plan, and write up a page for the D2 milestone. | Julie Flater | Complete | Complete |  | 2017-02-15 | 2 hrs | 2017-02-22 | 2017-02-20
2 | M2_D3 - Version Control | Set up the Github project for us and write up a page for the D3 milestone. | Muntaser Khan | Complete | Complete |  | 2017-02-15 | 2 hrs | 2017-02-22 | 2017-02-19
3 | M2_D4 - Task Policy | Create a project management tracking spreadsheet and write up a page for the D4 milestone. | Matt Conroy | Complete | Complete |  | 2017-02-15 | 2 hrs | 2017-02-22 | 2017-02-21
4 | M2_D5 -Liason | Assign a team liason for interactions with the prof. | Julie Flater | Complete | Complete |  | 2017-02-15 | < 1 hr | 2017-02-22 | 2017-02-20
5 | M2 - Schedule Rough Draft Review Mtg | Schedule our rough draft review meeting with the Professor. | Julie Flater | Complete | Complete |  | 2017-02-22 | < 1 hr | 2017-03-01 | 2017-03-08 | Met w/ Prof on Wed evening during class.
6 | M2-A D1 - Project Status | Maintain project tasks, estimates, effort, and status each week | Matt Conroy | In-Progress | Green |  | 2017-03-05 | 1 hr / wk | Ongoing
7 | M2-B D2 - DIM & FACT Metadata (Julie) | Independently review the Project documents and create a list of DIMs, DATTs, FACTs for review with the team | Julie Flater | Complete | Complete |  | 2017-02-22 | 6 hrs | 2017-03-05 | 2017-03-05
8 | M2-B D2 - DIM & FACT Metadata (Muntaser) | Independently review the Project documents and create a list of DIMs, DATTs, FACTs for review with the team | Muntaser Khan | Complete | Complete |  | 2017-02-22 | 6 hrs | 2017-03-05 | 2017-03-05
9 | M2-B D2 - DIM & FACT Metadata (Matt) | Independently review the Project documents and create a list of DIMs, DATTs, FACTs for review with the team | Matt Conroy | Complete | Complete |  | 2017-02-22 | 6 hrs | 2017-03-05 | 2017-03-05
10 | M2-B - Compare the DIMs to the OLTP Model and Fix | Julie will review the OLTP model and update our DIMs to match the D2 requirements and make sure the columns in our DIMs match what actually exist in the OLTP. | Julie Flater | In-Progress | Green |  | 2017-03-15 | 4 hrs | 2017-03-18
11 | M2-C - Compare the IDDs to the new DIMs and the OLTP model and fix | Matt will review the OLTP model and Julie's work on the DIMs and make sure our IDDs line up with these two structures. | Matt Conroy | In-Progress | Green |  | 2017-03-15 | 4 hrs | 2017-03-19
12 | M2-D D4 - ERD of the Physical Data Model | Create a strict, star schema ROLAP MDM physical data model using MS SQL 2012 as the physical db for this deliverable. | Muntaser Khan | Not Started (Dependent) |  |  | 2017-03-19 | 4 hrs | 2017-03-20
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199

## v3 - 19MAR17
| T22 - Project Management |  | v 3.0 | Updated 18.MAR.17 by MWC
No. | Task Name | Description | Project Owner | Status | Rating | Get-to-Green Plan | Date Started | Est. Effort | Est. Date of Completion | Act. Date of Completion | Notes
1 | M2_D2 - Communication Plan | Set up a OneDrive folder for the project team, formalize our communications plan, and write up a page for the D2 milestone. | Julie Flater | Complete | Complete |  | 2017-02-15 | 2 hrs | 2017-02-22 | 2017-02-20
2 | M2_D3 - Version Control | Set up the Github project for us and write up a page for the D3 milestone. | Muntaser Khan | Complete | Complete |  | 2017-02-15 | 2 hrs | 2017-02-22 | 2017-02-19
3 | M2_D4 - Task Policy | Create a project management tracking spreadsheet and write up a page for the D4 milestone. | Matt Conroy | Complete | Complete |  | 2017-02-15 | 2 hrs | 2017-02-22 | 2017-02-21
4 | M2_D5 -Liason | Assign a team liason for interactions with the prof. | Julie Flater | Complete | Complete |  | 2017-02-15 | < 1 hr | 2017-02-22 | 2017-02-20
5 | M2 - Schedule Rough Draft Review Mtg | Schedule our rough draft review meeting with the Professor. | Julie Flater | Complete | Complete |  | 2017-02-22 | < 1 hr | 2017-03-01 | 2017-03-08 | Met w/ Prof on Wed evening during class.
6 | M2-A D1 - Project Status | Maintain project tasks, estimates, effort, and status each week | Matt Conroy | In-Progress | Green |  | 2017-03-05 | 1 hr / wk | Ongoing
7 | M2-B D2 - DIM & FACT Metadata (Julie) | Independently review the Project documents and create a list of DIMs, DATTs, FACTs for review with the team | Julie Flater | Complete | Complete |  | 2017-02-22 | 6 hrs | 2017-03-05 | 2017-03-05
8 | M2-B D2 - DIM & FACT Metadata (Muntaser) | Independently review the Project documents and create a list of DIMs, DATTs, FACTs for review with the team | Muntaser Khan | Complete | Complete |  | 2017-02-22 | 6 hrs | 2017-03-05 | 2017-03-05
9 | M2-B D2 - DIM & FACT Metadata (Matt) | Independently review the Project documents and create a list of DIMs, DATTs, FACTs for review with the team | Matt Conroy | Complete | Complete |  | 2017-02-22 | 6 hrs | 2017-03-05 | 2017-03-05
10 | M2-B - Compare the DIMs to the OLTP Model and Fix | Julie will review the OLTP model and update our DIMs to match the D2 requirements and make sure the columns in our DIMs match what actually exist in the OLTP. | Julie Flater | In-Progress | Green |  | 2017-03-15 | 4 hrs | 2017-03-18
11 | M2-C - Compare the IDDs to the new DIMs and the OLTP model and fix | Matt will review the OLTP model and Julie's work on the DIMs and make sure our IDDs line up with these two structures. | Matt Conroy | In-Progress | Green |  | 2017-03-15 | 4 hrs | 2017-03-19
12 | M2-D D4 - ERD of the Physical Data Model | Create a strict, star schema ROLAP MDM physical data model using MS SQL 2012 as the physical db for this deliverable. | Muntaser Khan | Not Started (Dependent) |  |  | 2017-03-19 | 4 hrs | 2017-03-20

## v2 - 12MAR17
| T22 - Project Management |  | v 2.0 | Updated 12.MAR.17 by MWC
No. | Task Name | Description | Project Owner | Status | Rating | Get-to-Green Plan | Date Started | Est. Effort | Est. Date of Completion | Act. Date of Completion | Notes
1 | M2_D2 - Communication Plan | Set up a OneDrive folder for the project team, formalize our communications plan, and write up a page for the D2 milestone. | Julie Flater | Complete | Complete |  | 2017-02-15 | 2 hrs | 2017-02-22 | 2017-02-20
2 | M2_D3 - Version Control | Set up the Github project for us and write up a page for the D3 milestone. | Muntaser Khan | Complete | Complete |  | 2017-02-15 | 2 hrs | 2017-02-22 | 2017-02-19
3 | M2_D4 - Task Policy | Create a project management tracking spreadsheet and write up a page for the D4 milestone. | Matt Conroy | Complete | Complete |  | 2017-02-15 | 2 hrs | 2017-02-22 | 2017-02-21
4 | M2_D5 -Liason | Assign a team liason for interactions with the prof. | Julie Flater | Complete | Complete |  | 2017-02-15 | < 1 hr | 2017-02-22 | 2017-02-20
5 | M2 - Schedule Rough Draft Review Mtg | Schedule our rough draft review meeting with the Professor. | Julie Flater | Complete | Complete |  | 2017-02-22 | < 1 hr | 2017-03-01 | 2017-03-08 | Met w/ Prof on Wed evening during class.
6 | M2-A D1 - Project Status | Maintain project tasks, estimates, effort, and status each week | Matt Conroy | In-Progress | Green |  | 2017-03-05 | 1 hr / wk | Ongoing
7 | M2-B D2 - DIM & FACT Metadata (Julie) | Independently review the Project documents and create a list of DIMs, DATTs, FACTs for review with the team | Julie Flater | Complete | Complete |  | 2017-02-22 | 6 hrs | 2017-03-05 | 2017-03-05
8 | M2-B D2 - DIM & FACT Metadata (Muntaser) | Independently review the Project documents and create a list of DIMs, DATTs, FACTs for review with the team | Muntaser Khan | Complete | Complete |  | 2017-02-22 | 6 hrs | 2017-03-05 | 2017-03-05
9 | M2-B D2 - DIM & FACT Metadata (Matt) | Independently review the Project documents and create a list of DIMs, DATTs, FACTs for review with the team | Matt Conroy | Complete | Complete |  | 2017-02-22 | 6 hrs | 2017-03-05 | 2017-03-05
10 | M2-B - Compare the DIMs to the OLTP Model and Fix | Julie will review the OLTP model and update our DIMs to match the D2 requirements and make sure the columns in our DIMs match what actually exist in the OLTP. | Julie Flater | In-Progress | Green |  | 2017-03-15 | 4 hrs | 2017-03-18
11 | M2-C - Compare the IDDs to the new DIMs and the OLTP model and fix | Matt will review the OLTP model and Julie's work on the DIMs and make sure our IDDs line up with these two structures. | Matt Conroy | In-Progress | Green |  | 2017-03-15 | 4 hrs | 2017-03-19
12 | M2-D D4 - ERD of the Physical Data Model | Create a strict, star schema ROLAP MDM physical data model using MS SQL 2012 as the physical db for this deliverable. | Muntaser Khan | Not Started (Dependent) |  |  | 2017-03-19 | 4 hrs | 2017-03-20

## v1 - 5MAR17
| T22 - Project Management |  | v 1.0 | Updated 5.MAR.17 by MWC
No. | Task Name | Description | Project Owner | Status | Rating | Get-to-Green Plan | Date Started | Est. Effort | Est. Date of Completion | Act. Date of Completion | Notes
1 | M2_D2 - Communication Plan | Set up a OneDrive folder for the project team, formalize our communications plan, and write up a page for the D2 milestone. | Julie Flater | Complete | Complete |  | 2017-02-15 | 2 hrs | 2017-02-22 | 2017-02-20
2 | M2_D3 - Version Control | Set up the Github project for us and write up a page for the D3 milestone. | Muntaser Khan | Complete | Complete |  | 2017-02-15 | 2 hrs | 2017-02-22 | 2017-02-19
3 | M2_D4 - Task Policy | Create a project management tracking spreadsheet and write up a page for the D4 milestone. | Matt Conroy | Complete | Complete |  | 2017-02-15 | 2 hrs | 2017-02-22 | 2017-02-21
4 | M2_D5 -Liason | Assign a team liason for interactions with the prof. | Julie Flater | Complete | Complete |  | 2017-02-15 | < 1 hr | 2017-02-22 | 2017-02-20
5 | M2 - Schedule Rough Draft Review Mtg | Schedule our rough draft review meeting with the Professor. | Julie Flater | In-Progress | Yellow | Waiting for Prof Response | 2017-02-22 | < 1 hr | 2017-03-01 |  | Our first 3 dates were rejected, awaiting confirmation for one of our next 2 dates.
6 | M2-A D1 - Project Status | Maintain project tasks, estimates, effort, and status each week | Matt Conroy | Complete | Complete |  | 2017-03-05 | 1 hr / wk | Ongoing
7 | M2-B D2 - DIM & FACT Metadata (Julie) | Independently review the Project documents and create a list of DIMs, DATTs, FACTs for review with the team | Julie Flater | Complete | Complete |  | 2017-02-22 | 6 hrs | 2017-03-05 | 2017-03-05
8 | M2-B D2 - DIM & FACT Metadata (Muntaser) | Independently review the Project documents and create a list of DIMs, DATTs, FACTs for review with the team | Muntaser Khan | Complete | Complete |  | 2017-02-22 | 6 hrs | 2017-03-05 | 2017-03-05
9 | M2-B D2 - DIM & FACT Metadata (Matt) | Independently review the Project documents and create a list of DIMs, DATTs, FACTs for review with the team | Matt Conroy | Complete | Complete |  | 2017-02-22 | 6 hrs | 2017-03-05 | 2017-03-05
10 | M2-C D3 - IDD Details | Create a IDD for each DIM and all of their hierachies | All | In-Progress |  |  | 2017-03-05 | 3 hrs | 2017-03-07 |  | We will divide and conquer this independently and meet Tuesday evening to pull everything together.
11 | M2-D D4 - ERD of the Physical Data Model | Create a strict, star schema ROLAP MDM physical data model using MS SQL 2012 as the physical db for this deliverable. | TBD | Not Started (Dependent)

## v0.0 - 26FEB17
| T22 - Project Management |  | v 0 | Updated 26.FEB.17 by MWC
No. | Task Name | Description | Project Owner | Status | Rating | Get-to-Green Plan | Date Started | Est. Effort | Est. Date of Completion | Act. Date of Completion | Notes
1 | M2_D2 - Communication Plan | Set up a OneDrive folder for the project team, formalize our communications plan, and write up a page for the D2 milestone. | Julie Flater | Complete | Complete |  | 2017-02-15 | 2 hrs | 2017-02-22 | 2017-02-20
2 | M2_D3 - Version Control | Set up the Github project for us and write up a page for the D3 milestone. | Muntaser Khan | Complete | Complete |  | 2017-02-15 | 2 hrs | 2017-02-22 | 2017-02-19
3 | M2_D4 - Task Policy | Create a project management tracking spreadsheet and write up a page for the D4 milestone. | Matt Conroy | Complete | Complete |  | 2017-02-15 | 2 hrs | 2017-02-22 | 2017-02-21
4 | M2_D5 -Liason | Assign a team liason for interactions with the prof. | Julie Flater | Complete | Complete |  | 2017-02-15 | < 1 hr | 2017-02-22 | 2017-02-20

## Lists
Julie Flater | Complete | Green
Muntaser Khan | In-Progress | Yellow
Matt Conroy | Not Started | Red
TBD | Not Started (Dependent) | Complete
All